## Release Plan
Increment Plan
Incr. | Start | Days | End | Size | Status | Release Date | Goal
1 |  | 0 |  | 0
2 | #VALUE! | 0 | #VALUE! | 0
Template note: Increment plan is intended to collect individual sprints into larger releases. In smaller projects, this is not needed.
Sprint Plan
Sprint | Start | Days | End | Size | Status | Release Date | Goal | Increment
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
Unplanned
|  |  | Unallocated stories | 0

## Product Backlog
Product Backlog
Story ID | Story name | Status | Size | Sprint | Priority | User Story | User Type
1 | Creation de cellier | Planned |  | 1 | M | En tant qu'usager, je peux créer plusieurs celliers | Usager
2 | Gestion Utilisateur | Planned |  |  | M | En tant qu'administrateur, je peux gérer la liste des usagers | Administrateur
3 | Importation de bouteilles | Planned |  |  | M | En tant qu'administrateur, je peux importer les bouteilles du site de la SAQ | Administrateur
4 | Creation de compte | Planned |  | 1 | M | En tant qu'usager, je peux me créer un compte et le gérer | Usager
5 | Gestion de Cellier | Planned |  | 1 | M | En tant qu'usager, je peux gérer mon cellier personnel (ajout, modification, retrait de bouteille) | Usager
6 | Detail de bouteille | Planned |  |  | M | En tant qu'usager, je peux voir les détails complets d'une bouteille afin de décider si je veux l’ajouter à mon cellie | Usager
7 | Catalogue de Bouteille | Planned |  | 1 | M | En tant qu'usager, je peux voir une liste de bouteilles de vin afin de choisir celles que je souhaite ajouter à mes celliers | Usager
8 | Catalogue de Cellier | Planned |  |  | M | En tant qu'usager , je peux afficher le catalogue de cellier et en choisir un | Usager
9 | Recherche dans cellier | Planned |  |  | S | En tant qu'usager, je peux faire des recherches dans mon cellier par nom,par type, par quantité, par pays, par millésime, etc | Usager
10 | Tri dans le Cellier | Planned |  |  | S | En tant qu'usager, je peux trier mon cellier par nom, par type, par quantité, par pays, par millésime, etc | Usager
11 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre d'usager | Administrateur
12 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre,le nombre de cellier | Administrateur
13 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre de cellier par usager | Administrateur
14 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre de bouteille par cellier et par usager | Administrateur
15 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre de bouteille bu et partager dans un temps donné | Administrateur
16 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre de bouteille ajouté dans un temps donné | Administrateur
17 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre le nombre de nouvel usager | Administrateur
18 | Statistiques | Planned |  |  | S | En tant qu'administrateur, je peux connaitre la valeur total des bouteilles (tous, par usager, par cellier) | Administrateur
19 | Statistiques | Planned |  |  | S | En tant qu'administrateur, Je peux corriger les données erronées du catalogue importé | Administrateur
20 | Signaler des erreurs | Planned |  |  | S | En tant qu'usager, je peux indiquer des erreurs dans le catalogue aux administrateurs | Usager
21 | Creation de liste d'achats | Planned |  |  | S | En tant qu'usager, je peux créer une liste d'achat | Usager
22 | Laisser des notes de degustation | Planned |  |  | S | En tant qu'usager, je peux laisser des notes de dégustation sur les bouteilles que j'ai consommé. | Usager
Sort Product Backlog
Note on A4: Once a Story ID is given to a story, do not change that number or reuse it even if you delete the story.
Note on C4: Use the following statuses: Planned (or empty) Ongoing Done Removed The sheet uses the above statuses in the formatting and calculation formulas.
Note on D4: Story Points or Ideal Days
Note on E4: Create a release plan by assigning stories to planned sprints. If there are more stories in the backlog than in the plan, leave the remaining stories unassigned to sprints.
Note on F4: You may assign priorities to the stories, but keep in mind that priority does not always equal implementation order.

## PB Burndown
Product Backlog Burndown Chart
Original planned size |  |  | 60 |  | Sprint count | 1
Count trend from last |  |  | 3 | sprints | Trend sprint count | 1
[5 empty] | Trend offset | 0 | [9 empty] | Note:
Velocity (points per sprint) |  |  | 20 |  | Sprints in Trend | 1 | [9 empty] | In this chart, the tops of the bars show the amount of actual
Original estimate |  |  | 60 | [12 empty] | (or planned) implemented functionality at the beginning of each sprint.
3 | [15 empty] | The bottoms of the bars show the changes in project scope
Realized total average |  |  |  |  | Trend count | 1 | [9 empty] | (i.e. if the amount of story points
Average last 8 | [15 empty] | in the project increases, the bottoms move lower). The length
Avg. worst 3 in last 8 | [15 empty] | of the bars indicate the estimated size of the project at the
Trend | [15 empty] | beginning of each sprint.
[5 empty] | These hidden cells are used to draw the graph on this page. DO NOT DELETE! | [10 empty] | The red line indicates the current planned scope.
Predictions - Completion at the end of sprint…
Original estimate - Min |  |  | 1
Original estimate - Avg |  |  | 1
Original estimate - Max |  |  | 2 |  | Standard Dev. | 1
3
Realized average |  |  |  |  | LastPlanned | 1
Average last 8 |  |  |  |  | LastRealized | 1
Avg. worst 3 in last 8
Trend
Realized + St. Dev
Realized - St. Dev
[5 empty] | Trend | [7 empty] | Average Speeds
Sprint | Remain.Work | Planned Work | Realized Work | Current Total Size | Col top | Do not delete… |  | Col bottom | Trend Help | Raw Trend | Real Trend | Current Bottom | Realized | Last 8 | Worst 3 in Last 8
1 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | [9 empty] | 0 |  | 0
3 | [9 empty] | 0 |  | 0
4 | [9 empty] | 0 |  | 0
5 | [9 empty] | 0 |  | 0
6 | [9 empty] | 0 |  | 0
7 | [9 empty] | 0 |  | 0
8 | [9 empty] | 0 |  | 0
9 | [9 empty] | 0 |  | 0
10 | [9 empty] | 0 |  | 0
11 | [9 empty] | 0 |  | 0
12 | [9 empty] | 0 |  | 0
13 | [9 empty] | 0 |  | 0
14 | [9 empty] | 0 |  | 0
15 | [9 empty] | 0 |  | 0
16 | [9 empty] | 0 |  | 0
17 | [9 empty] | 0 |  | 0
18 | [9 empty] | 0 |  | 0
19 | [9 empty] | 0 |  | 0
20 | [9 empty] | 0 |  | 0
21 | [9 empty] | 0 |  | 0
22 | [9 empty] | 0 |  | 0
23 | [9 empty] | 0 |  | 0
24 | [9 empty] | 0 |  | 0
Note on B15: Average estimate * 0,6
Note on B17: Average estimate * 1,6
Note on B19: As of latest Product Backlog estimate

## Sp1
1
Sprint implementation days |  |  |  | Effort | Remaining on implementation day…
Trend calculated based on last |  | Days | Totals | 132 | 0
Task rows | 18 | Done days | 1 |  | 132 | #DIV/0! | #DIV/0!
Warning! These are necessary |  | Trend |  |  | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
template rows |  | Trend Days | 0 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3
Creation de Cellier | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Installation du systeme laravel php | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire la page HTML de la creation de Cellier | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Connexion de la page a la base de donnees | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire des controller pour inserer les donnees | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire des modales pour pour demonstration de succes | 1 | dev1 | Planned | 12 | 1: 0; 2: 0; 3: 0
Creation de compte | 4 | dev3 | Planned | 12 | 1: 0; 2: 0; 3: 0
Un bouton pour aller a la page de formulaire | 4 | dev3 | Planned | 12 | 1: 0; 2: 0; 3: 0
Creation de la page avec formulaire pour les informations de l'utilisateur | 4 | dev3 | Planned | 12 | 1: 0; 2: 0; 3: 0
Creation de routes | 4 | dev3 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire methode pour inserer donnees dans la base donnees | 4 | dev3 | Planned | 12 | 1: 0; 2: 0; 3: 0
Gestion de Cellier | 9 | dev5 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire un bouton pour modification de cellier | 9 | dev5 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire page HTML pour modification cellier | 9 | dev5 | Planned | 12 | 1: 0; 2: 0; 3: 0
Faire controller pour modifier table Cellier | 9 | dev5 | Planned | 12 | 1: 0; 2: 0; 3: 0
Inserer dans la BD | 4
Catalogue de Bouteille | 7
Gestion de Cellier | 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp2
2
Sprint implementation days | 6 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 6 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5; 6: 6
|  |  |  | 0 | 1: 0
|  |  |  | 0 | 1: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sp3
3
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 6 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
|  |  |  | 0 | 1: 0
|  |  |  | 0 | 1: 0
|  |  |  | 0 | 1: 0
|  |  |  | 0 | 1: 0
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.

## Sprint Sheet Template
1
Sprint implementation days | 5 |  |  | Effort | Remaining on implementation day…
Trend calculated based on last | 5 | Days | Totals | 0 | 0
Task rows | 1 | Done days | 1 |  | 0 | 0 | 0 | 0 | 0
Warning! These are necessary |  | Trend |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
template rows |  | Trend Days | 1 |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25
Task name | Story ID | Responsible | Status | Est. | 1: 1; 2: 2; 3: 3; 4: 4; 5: 5
Sort Sprint Tasks
Update Task Slips
Note on A9: Count only active working and implementation days. Do not include Planning Day or Sprint Review. E.g. a 4-week Sprint would most likely have 18 implementation days.